EXTRACTIVE INDUSTRY TRANSPARENCY INITIATIVE (EITI) WORKPLAN, 2006-2008

| OBJECTIVE 1: CARRY OUT AN INDEPENDENT AUDIT OF THE MINING INDUSTRY. |
| --- |
| INTENDED OUTPUT | ACTIVITY | TIMELINES | INDICATIVE COST | RESPONSIB - ILITY | OUTCOME/ CRITERIA LINKAGE |
| Appointment of an Independent Aggregator | 1.Advertisement of Expression of interest 2.Evaluation of Expression of Interest 3.Evaluation of Proposals | August, 2006 |  |  | Aggregator selected (Criteria 2,3&4) – For an audit to be carried out |
|  | Negotiation s of the Aggregator’s fee |  | [$180,000.00]* For two years (August., 2006- August, 2009) | MOFEP Funding to be provided by GOG . |  |
| Template to be Finalized | Discuss and finalize the designed Template with the Aggregator Agree on data and reporting mechanisms |  |  | Steering Committee/ Aggregator | Template finalized |
| Financial Audit to be conducted | Aggregator to collect information and analyze information. Report Preparation and discussion | [October- November] |  | Aggregator/ EITI Coordinating Secretariat | Audit Report - (Criteria 2,3&4) |
| OBJECTIVE 2 : PUBLICATION AND DISSEMINATION AUDIT REPORT |
| INTENDED OUTPUT | ACTIVITY | TIMELINES | INDICATIVE COST | RESPONSIB - ILITY | OUTCOME/ CRITERIA LINKAGE |
| Workshop to discuss the EITI Draft Financial Audit Report | Organize stakeholder workshop for experts to discuss the draft financial audit report | [November, 2006] | $20,000.00 | EITI Secretariat | Stakeholder workshop held (Criteria 5) |
| Audit Report Published | Preparation and publication of EITI Audit Report in both local and international papers and journals | [December, 2006] | $10,000.00 | EITI Secretariat | Audit Report Published ( Criteria 1) – Regular Publication |
| Ghana EITI Handbook published | Preparation and publication and distribution of Ghana EITI Handbook. Quarterly publication of EITI Newsletters. Development and printing of Fliers for awareness creation | December, 2006 Ongoing Ongoing | $10,000.00 $10,000.00 $10,000.00 | EITI Secretariat/DP EITI Secretariat/DP EITI Secretariat/DP | ( Criteria 1) – Regular Publication |
| EITI Website for Ghana created | Engage a Website designer Website Operational Management of the Website | June 2006 July, 2006 Ongoing |  | GTZ MOFEP have Identified a counterpart designer to work with GTZ - MOFEP staff to put in 3hrs a day | EITI Website Operational and to be managed by MOFEP Staff identified (Criteria 1&5) |
| 3- major EITI Public Information Centers Set up | Identify the Mining Communities Logistics for the First Information Centre 1 Computer 1 Printer Maintenance cost Logistics for the Second Centre 1 Computer 1 Printer Maintenance cost Third Centre set- up | July, 2006 – June, 2008 August, 2006 June, 2007 March, 2008 | $10,000.00 $2,000.00 $2,000.00 $1,000.00 $2,000.00 $2,000.00 $1,000.00 | MOFEP – EITI Secretariat District Assemblies to provide Offices and appoint staff | EITI information Centers set-up in 3 Communities (Criteria 5) |
| OBJECTIVE 3 : CAPACITY BUILDING AND AWARENESS CREATION |
| INTENDED OUTPUTS | ACTIVITY | TIMELINES | INDICATIVE COST | RESPONSIB- ILITY | OUTCOME/ CRITERIA LINKAGE |
| Strengthening of the EITI Secretariat MOFEP | A 6-man study tour to Nigeria for two weeks [Canada Peru] Botswana Conference Participation in International Conferences on EITI | August, 2006 July, 2006 October, 2006 | $36,000.00 | DPs DPs (DFID,GTZ, etc) | Secretariat Strengthened ( Criteria 1- 6) Development of the Work Plan Sustainability of the Initiative |
| Logistics to be provided to strengthen the EITI Secretariat | Provision of one cross country Vehicle for coordinating and trekking purposes .Computers (2), Printers (2) Photocopier (1) Laptop Computer (1) LCD Projector (1) Fax Machine (1) Operation Cost of Secretariat Vehicle Maintenance Fuel cost Utility cost Computers maintenance cost Stationary Incidentals | May, 2006- June, 2006 Ongoing | $25,000.00 $4,000.00 $4,000.00 $3,000.00 $3,000.00 $4,000.00 $1,000.00 $20,000.00 ($5,000) ($7,000) [$5,000]* ($5,000) [$5,000]* ($3,000) | DPs DPs DPs MOFEP MOFEP | Logistics Provided to strengthen the secretariat ( Criteria 6) |
| INTENDED OUTPUT | ACTIVITY | TIMELINES | INDICATIVE COST | RESPONSIB - ILITY | OUTCOME/ CRITERIA LINKAGE |
| Appointment of Program Manager | 1. Appoint a local program officer to run the Secretariat. 2. Office identified at the MOFEP building for the Program Manager 3. Office furnished | August, 2006 May, 2006 June, 2006 | $36,000.00 ($1,500 for two years) $2,000.00 | MOFEP/DPs MOFEP has already identified an office and will provide office furniture DPs | Program Manager Appointed |
| Technical Assistance to be provided to the Secretariat | Formal request for technical assistance made to DPs. | Ongoing |  | MOFEP |  |
| Awareness creation extended | 1. DCEs and Chiefs in Four Mining Regions( Western, Eastern Brong Ahafo and Ashanti.) 2.Parliamentary committee on Mines and Forestry 3.Civil Society Organizations and other major stakeholders | May-June 2006 August, 2006 November 30, 2006 | $20,000.00 $10,000.00 ($20,000.00) | MOFEP/DPs MOFEP/DPs MOFEP/DPs GTZ | Main stakeholders fully sensitized ( Criteria 5& 6) |
| Capacity building for Civil Society And District Assemblies | Organize 3 - capacity building Training Workshops -A detailed capacity building workshop | July, 2006 – December,2007 | $10,000.00 $10,000.00 | MOFEP/DIST-RICT ASSEMBLIES / CSOs MOFEP/DPs | Capacity Available for EITI Implementation. ( Criteria 5&6) |
| INTENDED OUTPUT | ACTIVITIES | TIMELINES | INDICATIVE COST | RESPONSIB- ILITY | OUTCOME/ CRITERIA LINKAGE |
| Development of Linkages between EITI and other governance initiatives | Analytical Work on the linkages i.e. IMF governance initiatives, Publish what you pay etc. | August, 2006 –June, 2007 | $10,000.00 | EITI Secretariat/ DPs | EITI well aligned with other governance initiatives - A proper framework developed to integrate and harmonize EITI with other governance initiatives |
| Development of a detailed EITI Communication Strategy | Consultant hired to develop a strategy and an Action Plan for communication | July, 2006 | $10,000.00 | EITI Secretariat | EITI Communication Strategy Action Plan Developed (Criteria 5&6) |
| OBJECTIVE 4: LEGISLATION OF EITI |
| Legislation Developed to make EITI compulsory for companies | 1.A Cabinet Paper from the Ministry of Finance proposing the need for legislation 2. Ministry of Mines and AGs Department to draft legislation | August-December, 2006 |  | MOFEP/ Parliament/ Ministry of Mines/ AGs Department |  |
| Develop Monitoring and Evaluation Strategy for EITI | Monitoring and Evaluation Action Plan Monitoring and Evaluation indicators | August, 2006 |  | EITI Secretariat/ Aggregator | Monitoring and Evaluation Action Plan developed internal evaluation of Ghana’s EITI |
| TOTAL COST |  |  | $278,000.00 |  |  |

*MOFEP to be responsible for those costs.